## Tracker
PERPETUAL OFFER WORKPLAN |  |  |  | Note: milestones keeping the status quo (e.g, "continue using legacy website") are not included |  | Phase | Milestone
Current as of: |  | 2018-10-22 |  |  |  | Phase 1 | Borgata Opera conversion
|  |  |  | Red denotes overlap with Customer Friction timeline |  | Phase 2 | ICE go-live for Springfield at Borgata Call Center
[6 empty] | Phase 3 | Perpetual offer and dynamic calendar go-live for Springfield
[6 empty] | Phase 4 | Perpetual offer and ICE go-live for NH, Beau, & GS @ Beau Call Center
[6 empty] | Phase 5 | Borgata DMP conversion and ICE Phase 2 rollout, sunset CCA
[6 empty] | Phase 6 | Perpetual offer and ICE Phase 3 rollout @ LV Call Center & property marketing
To add status column
ID | Phase | Property | Workstream | Milestone or Task | Start Date | Due Date | Owner | Details/Notes/ Dependencies
1 | Phase 1 | Borgata | GSE | Web layer interfaces with ACSC (to grab ratings/segments) | Ongoing | 2018-05-08 | Buttery/Forelli
2 | Phase 1 | Borgata | GSE | Web layer interfaces with GSE (to provide GSE with ratings/segment) | Ongoing | 2018-05-08 | Buttery/Forelli | Is GSE feeding CCA + Web for Borgata at the moment?
3 | Phase 1 | Borgata | GSE | GSE/Mystique configured with booking limits | Ongoing | 2018-05-08 | Buttery/Forelli
4 | Phase 2 | Springfield | Agent | Sharepoint set up to provide agent with customer rating/segment based on ID | TBD | 2018-06-06 | Forelli (+ option to add) | Sam provides algorithm to IT; Full integration of Teradata/CVS interface will not exist by 6/6
5 | Phase 2 | Springfield | DM / RM | Define property specific booking limits (Springfield) | TBD | 2018-06-06 | Stratton + Anika
6 | Phase 2 | Springfield | GSE | Configure property-specific booking limits (in addition to new property setup of rate codes, etc.) | TBD | 2018-06-06 | Buttery/Forelli | Cross-property booking limits due 5/11
7 | Phase 2 | Springfield | Agent | ICE, dynamic calendar available for booking (with manual component of adding rank to ICE) | TBD | 2018-06-06 | Buttery/Forelli | Will require manual component; will not have DMP calendar
8 | Phase 2 | Springfield | Agent | ICE/Friction PHASE 1 Enhancements: - High priority comments - Search by name and date of birth - Patron offer status - Restaurants configured - Taxes and fees configured | TBD | 2018-06-06 | Buttery/Forelli
9 | Phase 2 | Springfield | Change | Formal training | 2018-06-06 | 2018-07-01 | TBD
10 | Phase 2 | Springfield | Go live | Agents begin taking reservations for Springfield | n/a | 2018-07-01 | n/a | No web transactions at this time for guests
11 | Phase 3 | Springfield | UX / Web | Dynamic, property specific calendar available via property website for guests to view and book rates | TBD | TBD | O'Neill | This is dependent on ICE calendar working; need to rollout together - early target of 9/1 via Forelli
12 | Phase 3 | Springfield | CVS | Requirements complete for CVS development for Regional build | 2018-04-15 | 2018-05-16 | Buttery/Clifford | Dustin to put together timeline w/ dependencies by 5/10 based on current info available All Customers need to be valued for Springfield
13 | Phase 3 | Springfield | CVS | Development and interface to Teradata to pull in guest rating/segment | TBD | 2018-06-06 | Buttery/Clifford | Development done, currently being tested
14 | Phase 3 | Springfield | CVS | CVS interface with GSE (to provide GSE with ratings/segment) | TBD | 2018-06-06 | Buttery/Clifford
15 | Phase 3 | Springfield | DM / RM | Customer valuation model for MGM guests visiting first time/and going forward complete | TBD | 2018-06-06 | Stratton/Khan | New Springfield guests + Regional -> Springfield guests
16 | Phase 3 | Springfield | DM / RM | QA procedure for customer valuation number/data | TBD | TBD | Stratton/Khan
17 | Phase 3 | Springfield | DM / RM | Rollout new customer offer/communication strategy |  | TBD | Property + Romard
18 | Phase 3 | Springfield | Agent | ICE, dynamic calendar available for booking (fully automated) | TBD | TBD | Buttery/Clifford | This is dependent on web calendar working; need to rollout together
19 | Phase 3 | Springfield | Go live | Web transactions are available to guests |  | TBD | n/a
20 | Phase 4 | Beau, Tunica, NH | DM / RM | Regional cross-property valuations complete |  | TBD + 45days | Stratton/Khan | All customers of MGM must have a value for each regional property at this point (cross property/default valuation complete for customers with play); Need to update springfield and borgata if necessary
21 | Phase 4 | Beau, Tunica, NH | CVS | Test CVS interface for additional properties |  | TBD + 45days | Buttery/Clifford
22 | Phase 4 | Beau, Tunica, NH | DM / RM | Define property specific booking limits (beau/tunica/NH) |  | 2018-05-09 | Stratton + Property Marketing VPs
23 | Phase 4 | Beau, Tunica, NH | GSE | Add property-specific booking limits |  | TBD + 45days | Buttery/Clifford | Cross property booking limits considered and included if warranted
24 | Phase 4 | Beau, Tunica, NH | UX / Web | Dynamic, property specific calendar available via property website for guests to view and book rates |  | TBD + 45days | O'Neill | This is dependent on ICE calendar; need to rollout together
25 | Phase 4 | Beau, Tunica, NH | Agent | ICE, dynamic calendar provided to Biloxi team |  | TBD + 45days | Buttery/Clifford | This is dependent on web calendar; need to rollout together
26 | Phase 4 | Beau, Tunica, NH | Agent | ICE PHASE 2: -Show events/tickets inventory -Event booking capability -Party and split discovery -Profile search: partial search, select system search -Reservation search: allow partial name (Opera) |  | TBD + 45days | Buttery/Clifford
27 | Phase 4 | Beau, Tunica, NH | Change | Formal training |  | TBD + 45days | TBD
28 | Phase 4 | Beau, Tunica, NH | DM / RM | QA procedure for customer valuation number/data |  | TBD + 45days | Stratton/Khan
29 | Phase 4 | Beau, Tunica, NH | Go live | Agents switch to using new ICE booking system |  | TBD + 45days | n/a | Currently using Opera/Patron
30 | Phase 4 | Beau, Tunica, NH | DM / RM | Rollout new customer offer/communication strategy |  | TBD + 45days | Property + Romard
31 | Phase 5 | Borgata | GSE | Borgata move to DMP |  | TBD + 90days | Lee/Forelli | Dining and events live on sitecore still, move rooms to DMP? | To discuss w/ Forelli
32 | Phase 5 | Borgata | UX / Web | Dynamic, property specific calendar available via property website for guests to view and book rates |  | TBD + 90days | O'Neill
33 | Phase 5 | Borgata | CVS | Interface between CVS and ACSC to pull segment/ratings |  | TBD + 90days | Buttery/Clifford | This replaces web layer interface? | To discuss w/ Forelli
34 | Phase 5 | Borgata | Agent | ICE PHASE 1-2 rollout; Move off of CCA |  | TBD + 90days | Buttery/Clifford | This assumes Borgata still using CCA up to this point right? Do we want to add Phase 3 ICE here? (likely keep as is) | To discuss w/ Forelli
35 | Phase 5 | Borgata | Agent | ICE, dynamic calendar provided to Borgata |  | TBD + 90days | Buttery/Clifford | Sam and Calvin need to chat regarding "defaults"
36 | Phase 5 | Borgata (Springfield) | Agent | ICE PHASE 2 rollout and training |  | TBD + 90days |  | Springfield and Borgata taking calls together
37 | Phase 5 | Borgata | Go live | Agents switch to using new ICE booking system |  | TBD + 90days | n/a | Currently on CCA
38 | Phase 6 | Las Vegas | DM / RM | Rollout new customer offer/communication strategy |  | TBD + 150days | Gatten | Hotel decoupled from all other offers
39 | Phase 6 | Las Vegas | CVS | Interface between CVS and predictive model/file |  | TBD + 150days | Buttery/Clifford
40 | Phase 6 | Las Vegas | DM / RM | Define property specific booking limits (LV) |  | 2018-05-09 | Gatten
41 | Phase 6 | Las Vegas | GSE | Any additional property booking limits |  | TBD + 150days | Buttery/Clifford
42 | Phase 6 | Las Vegas | UX / Web | MGMResorts, Mlife, and all property websites updated for dynamic calendar |  | TBD + 150days | O'Neill | The addition of a view that shows mulitproperty calendar
43 | Phase 6 | Las Vegas | Agent | ICE Phase 1,2, and 3 enhancements + dynamic calendar provided to Vegas call centers |  | TBD + 150days | Buttery/Clifford | All VIP call centers, main call center
44 | Phase 6 | Las Vegas | Change | Formal training |  | TBD + 150days
45 | Phase 6 | Las Vegas | Go live | Agents switch to using new ICE booking system |  | TBD + 150days | n/a
Not Started
On Track
Monitor
At Risk
Completed