## Tracker
PERPETUAL OFFER WORKPLAN |  |  |  | Note: milestones keeping the status quo (e.g, "continue using legacy website") are not included |  | Phase | Milestone
Current as of: |  | 2018-09-18 |  |  |  | Phase 1 | Borgata Opera conversion
|  |  |  | Red denotes overlap with Customer Friction timeline |  | Phase 2 | ICE go-live for Springfield at Borgata Call Center
[6 empty] | Phase 3 | Perpetual offer and dynamic calendar go-live for Springfield
[6 empty] | Phase 4 | Perpetual offer and ICE go-live for NH, Beau, & GS @ Beau Call Center
[6 empty] | Phase 5 | Borgata DMP conversion and ICE Phase 2 rollout, sunset CCA
[6 empty] | Phase 6 | Perpetual offer and ICE Phase 3 rollout @ LV Call Center/Gold Strike & property marketing
ID | Phase | Property | Workstream | Milestone or Task | Start Date | Due Date | Owner | Details/Notes/ Dependencies
1 | Phase 1 | Borgata | GSE | Web layer interfaces with ACSC (to grab ratings/segments) | Ongoing | 2018-05-08 | Buttery/Forelli | Complete
2 | Phase 1 | Borgata | GSE | Web layer interfaces with GSE (to provide GSE with ratings/segment) | Ongoing | 2018-05-08 | Buttery/Forelli | Complete
3 | Phase 1 | Borgata | GSE | GSE/Mystique configured with booking limits | Ongoing | 2018-05-08 | Buttery/Forelli | Complete
4 | Phase 2 | Springfield | Agent | Sharepoint set up to provide agent with customer rating/segment based on ID | TBD | 2018-06-06 | Forelli (+ option to add) | Sam provides algorithm to IT; Full integration of Teradata/CVS interface will not exist by 6/6
5 | Phase 2 | Springfield | DM / RM | Define property specific booking limits (Springfield) | TBD | 2018-06-06 | Stratton + Anika
6 | Phase 2 | Springfield | GSE | Configure property-specific booking limits (in addition to new property setup of rate codes, etc.) | TBD | 2018-06-06 | Buttery/Forelli
7 | Phase 2 | Springfield | Agent | ICE, dynamic calendar available for booking (with manual component of adding rank to ICE) + ICE PHASE 1 Enhancements | TBD | 2018-06-06 | Buttery/Forelli | Will require manual component; will not have DMP calendar
8 | Phase 2 | Springfield | Change | Agent Training complete | 2018-06-06 | 2018-07-01 | TBD
9 | Phase 2 | Springfield | Milestone | Agents begin taking reservations for Springfield | n/a | 2018-07-01 | n/a | No web transactions at this time for guests
10 | Phase 3 | Regional | CVS | Requirements complete for CVS development for Regional build | 2018-04-15 | 2018-05-16 | Buttery/Clifford | Dustin to put together timeline w/ dependencies by 5/10 based on current info available All Customers need to be valued for Springfield
11 | Phase 3 | Springfield | DM / RM | Customer valuation model for MGM guests visiting first time/going forward | TBD | 2018-06-06 | Stratton/Khan | New Springfield guests + Regional -> Springfield guests
12 | Phase 3 | Regional | CVS | Detailed design complete (Regional) | Ongoing | 2018-06-20 | Buttery/Clifford
13 | Phase 3 | Regional | UX / Web | Detailed design complete (Single Property) | Ongoing | 2018-07-31 | O'Neill | Design draft review 7/5
14 | Phase 3 | Regional | CVS | CVS Development complete (Regional) | 2018-05-29 | 2018-08-03 | Buttery/Clifford | Development and CVS interface to Teradata to pull in guest rating/segment;CVS interface with GSE (to provide GSE with ratings/segment)
15 | Phase 3 | Regional | UX / Web | Development complete (Single Property) | 2018-08-08 | 2018-09-18 | O'Neill
16 | Phase 3 | Regional | CVS | QA CVS procuedre complete (Regional) | TBD | 2018-09-21 | Buttery/Clifford
17 | Phase 3 | Regional | UX / Web | QA UX procedure complete (Single Property) | TBD | 2018-09-28 | O'Neill
18 | Phase 3 | Springfield | DM / RM | QA Customer valuation | TBD | 2018-09-28 | Stratton/Khan
19 | Phase 3 | Springfield | DM / RM | Rollout new customer offer/communication |  | 2018-09-30 | Property + Romard
20 | Phase 3 | Springfield | Agent | ICE, dynamic calendar available for booking (fully automated) | TBD | 2018-10-02 | Buttery/Clifford | This is dependent on web calendar working; need to rollout together
21 | Phase 3 | Regional | Milestone | CVS for Regionals Ready |  | 2018-09-28 | Buttery/Clifford
22 | Phase 3 | Regional | Milestone | Single Property Calendar Complete / Online |  | 2018-10-02 | O'Neill | Rolling out with ICE
23 | Phase 3 | Springfield | Milestone | Go Live - perpetual/calendar (Springfield) |  | 2018-10-03 | n/a
24 | Phase 4 | Beau, Tunica, NH | DM / RM | Define property specific booking limits (beau/tunica/NH) |  | 2018-05-09 | Stratton + Property Marketing VPs | Complete??
25 | Phase 4 | Beau, Tunica, NH | DM / RM | Regional cross-property valuations complete |  | 2018-09-30 | Stratton/Khan | All customers of MGM must have a value for each regional property at this point (cross property/default valuation complete for customers with play); Need to update springfield and borgata if necessary
26 | Phase 4 | Beau, Tunica, NH | Agent | ICE, dynamic calendar available for booking |  | 2018-11-01 | Buttery/Clifford | This is dependent on web calendar; need to rollout together
27 | Phase 4 | Beau, Tunica, NH | CVS | QA CVS procuedre complete | TBD | 2018-11-01 | Buttery/Clifford | Add booking limits specific to properties, etc.
28 | Phase 4 | Beau, Tunica, NH | UX / Web | QA UX procedure complete | TBD | 2018-11-02 | O'Neill
29 | Phase 4 | Beau, Tunica, NH | DM / RM | QA Customer valuation | TBD | 2018-11-02 | Stratton/Khan
30 | Phase 4 | Beau, Tunica, NH | DM / RM | Rollout new customer offer/communication strategy |  | 2018-11-07 | Property + Romard
31 | Phase 4 | Beau, Tunica, NH | Change | Agent Training (ICE enhancements + Perpetual) complete |  | 2018-11-07 | TBD
32 | Phase 4 | Beau, Tunica, NH | Milestone | Go Live - perpetual/calendar (beau/tunica/NH) |  | 2018-11-08 | n/a
33 | Phase 6 | LV/Gold Strike | DM / RM | Define property specific booking limits (LV) |  | 2018-06-06 | Gatten
34 | Phase 6 | LV/Gold Strike | UX / Web | UX design complete (Multi Calendar) | 2018-06-30 | 2018-09-15 | O'Neill | Design draft review 8/15
35 | Phase 6 | LV/Gold Strike | CVS | Interface between CVS and predictive model/file | TBD | 2018-10-15 | Buttery/Clifford | CVS development complete
36 | Phase 6 | LV/Gold Strike | UX / Web | UX dev complete (Multi Calendar) | 2018-10-06 | 2018-11-13 | O'Neill
37 | Phase 6 | LV/Gold Strike | CVS | QA CVS procuedre complete (Vegas) | TBD | 2018-11-20 | Buttery/Clifford
38 | Phase 6 | LV/Gold Strike | UX / Web | QA UX procedure complete (Multi Property) | TBD | 2018-11-26 | O'Neill
39 | Phase 6 | LV/Gold Strike | DM / RM | QA Customer valuation | 2018-10-10 | 2018-11-26 | Stratton/Khan/Chan
40 | Phase 6 | LV/Gold Strike | Agent | ICE Phase 1,2, and 3 enhancements + dynamic calendar provided to Vegas call centers |  | 2018-11-26 | Buttery/Clifford | All VIP call centers, main call center
41 | Phase 6 | LV/Gold Strike | DM / RM | Rollout new customer offer/communication strategy | TBD | 2018-12-10 | Gatten | Hotel decoupled from all other offers
42 | Phase 6 | LV/Gold Strike | Change | Agent Training (ICE enhancements + Perpetual) complete | TBD | 2018-12-10
43 | Phase 6 | LV/Gold Strike | Milestone | Go Live - perpetual/calendar (LV/GoldStrike) |  | 2018-12-12 | n/a | The addition of a view that shows mulitproperty calendar

## Borgata TBD
ID | Phase | Property | Workstream | Milestone or Task | Start Date | Due Date | Owner | Details/Notes/ Dependencies
35 | Phase 5 | Borgata | Agent | ICE, dynamic calendar provided to Borgata |  | 2018-11-01 | Buttery/Clifford | Sam and Calvin need to chat regarding "defaults" | Kill Borgata?
36 | Phase 5 | Borgata | CVS | Interface between CVS and ACSC to pull segment/ratings |  | 2018-11-15 | Buttery/Clifford | This replaces web layer interface?
37 | Phase 5 | Borgata (Springfield) | Agent | ICE PHASE 2 rollout and training | TBD | 2018-11-30 |  | Springfield and Borgata taking calls together
38 | Phase 5 | Borgata | GSE | Borgata move to DMP |  | 2018-12-01 | Lee/Forelli | Dining and events live on sitecore still, move rooms to DMP?
39 | Phase 5 | Borgata | UX / Web | Dynamic, property specific calendar available via property website for guests to view and book rates |  | 2018-12-01 | O'Neill
40 | Phase 5 | Borgata | Agent | ICE PHASE 1-2 rollout; Move off of CCA |  | 2018-12-01 | Buttery/Clifford | This assumes Borgata still using CCA up to this point right? Do we want to add Phase 3 ICE here? (likely keep as is)
41 | Phase 5 | Borgata | Milestone | Agents switch to using new ICE booking system |  | 2018-12-01 | n/a | Currently on CCA